## Slide 1: Alpha Manufacturing Group(AMG)
Recommended Approach for the ERM Transformation Case
David Tetteh Ankrah
23rd May 2026

## Slide 2: Current State Overview
Core ERP : Finance, Manufacturing/MRP, Procurement (~80 users).
Financial: 80% of custom order saw margin erosion last year.
Operational: BOM sync failures are causing manufacturing delays.
Technology: Core ERP is 20 years old; landscape is fragmented and Excel-heavy.

## Slide 3: Project Objectives
The objectives listed in order are:
Ensuring daily operations run during the transition.
Delivery of reliable margin visibility on custom orders.
Fixing the engineering-to-ERP data flow.
Simplifying the application landscape and reducing heavy Excel reliance and building a foundation for future improvements.

## Slide 4: Recommended Approach
A phased, 12-month project with a narrow first go-live. The various phases are:
Phase 1(Months 1-3): Discovery and Design.
Phase 2(Months 3-7): Building and Configuration.
Phase 3(Months 7-10): Training and Testing.
Phase 4(Months 10-12): Cutover Stage and Care Period.

## Slide 5: Initial Scope
IN for first go-live | OUT for first go-live(deferred to phase two)
Core finance functions Order-to-cash flow Manufacturing and MRP Engineering-to-ERP integration(BOMs) | CRM integration HRIS and payroll integration Advanced analytics Supplier and customer portals

## Slide 6: Controlling Scope and Customization
Use only the defined ERP process unless it goes against a documented business reason.
Customizations are only approved by the Steering Committee, not by individual stakeholders.
Non-essential features for go-live go to phase two automatically.

## Slide 7: Data Migration Strategy
Master data(customers, vendors etc.) and transactions from past two years are fully migrated.
Closed orders and jobs from past two years are only accessible in summary form.
Everything older than eight years is stored in a separate archive, read-only access is available to finance and audit.

## Slide 8: Data and Reporting
Bridge reports to pull data from both ERPs into one view during the transition.
Run a parallel close in both systems for the first month after go-live, reconcile before declaring new ERP as the source of truth.

## Slide 9: Risks and How they will be managed
Scope creep: Enforcing the phase two backlog rule mentioned earlier.
Poor data quality: Data cleanup starts before data migration to prevent inconsistencies.
Customization indiscipline: Ensuring changes are only approved by the Steering Committee.

## Slide 10: Next steps if approach is approved
Mobilization of project team, appointment of executive sponsor and steering committee.
ERP vendor shortlist created and demo sessions scheduled.
End of Month 1: Erp vendor selected and contract signed.
End of Month 2: Detailed scope documentation and approval of project charter.
End of Month 3: Phase 1 complete, Phase 2 underway.

## Slide 11: Summary
A phased 12-month project with a narrow first go-live.
Initial scope: Finance, Manufacturing, Procurement, BOM integration, margin reporting.
Three major risks were identified in the recommendation, finance and reporting are protected throughout the project.